## Overview
Mongo-free SQL migration
As of | 2026-10-02
Rule | Existing SQL objects only. No DDL or migrations.
Update process | When a migration task is completed, set Status to Done and fill Completed Date and Evidence / Notes.
Progress | Count / Value
Total tasks | 88
Completed | 53
In progress | 4
Blocked | 20
Not started | 11
Completion | 60.23%
Open blockers | 8
How to maintain this tracker
Update the matching task row after implementation and verification. Set Status, Completed Date and Evidence / Notes. Keep blocked tasks open until the stated SQL-schema evidence or product decision is recorded. No database schema changes are allowed.

## Tasks
Task ID | Phase | Work package | Task | Acceptance / evidence | Dependencies | Status | Owner | Target date | Completed date | Evidence / notes
SQL-001 | 0. Freeze SQL contract and create evidence | 0.1 Verify databases and schema without writes | Confirm the configured SSS connection and any already-configured ERP SQL connection, database names, and read/write identities. | there is a current metadata snapshot and a reviewed list of allowed existing tables/columns; no data or schema was changed. | None | Done |  |  | 2026-10-02 | Verified read-only connection to SSS_copy as erp_readonly; check returned dbo.stockdetails=80,997 and dbo.newproduct=224. Metadata checks confirmed erp_pos_writer connects to SSS_copy, can INSERT dbo.sales2 and dbo.salsntry and UPDATE dbo.newproduct. Both identities lack CREATE TABLE and ALTER ANY SCHEMA. Separate ERP SQL credentials are not configured; check:erp-sql stopped because ERP_SQL_DB_NAME is missing. No SQL writes or DDL were performed.
SQL-002 | 0. Freeze SQL contract and create evidence | 0.1 Verify databases and schema without writes | Make application credentials unable to perform DDL where deployment allows: deny schema creation/alteration and migration permissions. | there is a current metadata snapshot and a reviewed list of allowed existing tables/columns; no data or schema was changed. | None | Blocked |  |  | 2026-10-02 | Read-only permission check: erp_admin connects to SSS_copy as dbo and is sysadmin/db_owner/db_ddladmin with CREATE TABLE, CREATE SCHEMA, ALTER ANY SCHEMA/USER/ROLE, and CONTROL. Backend loads these credentials and invokes ensureErpDbAccess at startup and during access recovery; it creates/alters database users and grants. Regular erp_readonly and erp_pos_writer logins lack schema DDL, but elevated runtime provisioning remains enabled. No writes, grants, or schema changes were executed.
SQL-003 | 0. Freeze SQL contract and create evidence | 0.1 Verify databases and schema without writes | Refresh table/column/key/index metadata and approximate row counts using read-only queries; compare with docs/mongo-to-sql-live-schema/schema-report.json. | there is a current metadata snapshot and a reviewed list of allowed existing tables/columns; no data or schema was changed. | None | Done |  |  | 2026-10-02 | Read-only schema discovery refreshed SSS_copy metadata on 2026-10-02: 503 tables, 17,285 columns, 183 tables with rows, 3 foreign keys, and 677 programmable objects. Compared against docs/mongo-to-sql-live-schema/schema-report.json: all 503 table names and all column-name sets match; no added/missing tables or column differences. Snapshot: backend/textilesoft-discovery/schema-SSS_copy/schema.json. SQL-001 connection evidence confirms SSS_copy row counts for stockdetails (80,997) and newproduct (224). Metadata-only SELECTs; no writes or DDL.
SQL-004 | 0. Freeze SQL contract and create evidence | 0.1 Verify databases and schema without writes | Verify required existing erp.* objects used by runtime SQL paths are present. Do not apply their repository migrations if absent. | there is a current metadata snapshot and a reviewed list of allowed existing tables/columns; no data or schema was changed. | None | Blocked |  |  | 2026-10-02 | Read-only comparison of SQL references in backend/src with the 2026-10-02 SSS_copy snapshot found 3 referenced objects absent from live erp schema: erp.sales_idempotency (sqlPosWriter), erp.sales_return_allocation (sqlPosWriter/sqlReturnsAudit), and erp.supplier_group_member (sqlPartyReports). Other referenced erp tables are present. No migrations or DDL were applied; B-02 covers the POS tables, supplier_group_member is an additional report-path blocker.
SQL-005 | 0. Freeze SQL contract and create evidence | 0.1 Verify databases and schema without writes | For each candidate table, document primary/business key, uniqueness evidence, nullability, relevant foreign keys, data types, tenant/branch scope, and semantic owner. | there is a current metadata snapshot and a reviewed list of allowed existing tables/columns; no data or schema was changed. | None | Done |  |  | 2026-10-02 | Generated docs/mongo-to-sql-live-schema/SQL_CANDIDATE_TABLE_EVIDENCE_2026-10-02.md from the live SSS_copy snapshot. Covers 62 distinct dbo/erp objects referenced in static backend SQL with columns/types/nullability/defaults/identity, PK and unique-index evidence, FK links, approximate rows, tenant/branch/location candidate columns, and source-file runtime owners. Three missing erp objects are explicitly identified. Business semantics are not inferred from names and remain a page-level follow-up; no row data or DDL was used.
SQL-006 | 0. Freeze SQL contract and create evidence | 0.1 Verify databases and schema without writes | Record unavailable database access or unverified table semantics as a blocker; do not infer compatibility from a table name. | there is a current metadata snapshot and a reviewed list of allowed existing tables/columns; no data or schema was changed. | None | Done |  |  | 2026-10-02 | Recorded observed blockers without inferring SQL compatibility: B-01 through B-06 cover unproven customer key, missing POS SQL objects, document lifecycles, finance ledger semantics, legacy UI/API paths, and HR/audit/sync/marketing targets. Added B-07 for elevated runtime admin credentials and B-08 for the absent separate ERP_SQL connection; updated B-02 with missing supplier_group_member. No data or schema changes.
SQL-007 | 0. Freeze SQL contract and create evidence | 0.2 Inventory all pages, endpoints and runtime entry points | Export the UI screen list from menu, route definitions, module registry and nested navigation. | every menu page and every Mongo model/query/write has a named disposition and no untraced runtime entry point remains. | None | Done |  |  | 2026-10-02 | Created docs/MONGO_FREE_SQL_SCREEN_INVENTORY_2026-10-02.md from menu.config.ts, RouteDefinitions.tsx, ModuleRegistry.ts, and ModuleRenderer.tsx: 119 menu entries with nesting, 133 direct route paths, 142 lazy registry entries, 208 unique viewMode keys. Includes path-to-module/redirect data and documents permission filtering, duplicate/alias routes, and fallback behavior. Static UI inventory only; API/DB tracing remains later work.
SQL-008 | 0. Freeze SQL contract and create evidence | 0.2 Inventory all pages, endpoints and runtime entry points | For every screen, trace UI component → API method/path → route mount → controller → service/repository → SQL table or Mongo model. | every menu page and every Mongo model/query/write has a named disposition and no untraced runtime entry point remains. | None | In Progress |  |  |  | Completed the source inventory of menu IDs, nested navigation, route paths and lazy modules. Full screen-specific UI API → mounted route → controller/service → SQL/Mongo mapping is still outstanding; see docs/MONGO_FREE_SQL_SCREEN_INVENTORY_2026-10-02.md and docs/MONGO_FREE_RUNTIME_ENTRYPOINT_AUDIT_2026-10-02.md.
SQL-009 | 0. Freeze SQL contract and create evidence | 0.2 Inventory all pages, endpoints and runtime entry points | Include background jobs, timers, queue workers, websocket handlers, sync, restore, scheduled tasks and startup/shutdown imports. | every menu page and every Mongo model/query/write has a named disposition and no untraced runtime entry point remains. | None | Done |  |  | 2026-10-02 | Static runtime-entrypoint review documented in docs/MONGO_FREE_RUNTIME_ENTRYPOINT_AUDIT_2026-10-02.md: active SQL-only server mounts/startup/shutdown, browser offline sync/timers, unmounted restore route, unreferenced queue/audit/cache modules, and no backend WebSocket/cron worker found. SQL admin bootstrap path remains separately blocked as B-07.
SQL-010 | 0. Freeze SQL contract and create evidence | 0.2 Inventory all pages, endpoints and runtime entry points | Mark every path SQL complete, SQL partial, Mongo legacy, no API, external integration, or blocked: no compatible SQL object. | every menu page and every Mongo model/query/write has a named disposition and no untraced runtime entry point remains. | None | In Progress |  |  |  | Classified current SQL-only mount groups and known legacy/unavailable path groups in docs/MONGO_FREE_RUNTIME_ENTRYPOINT_AUDIT_2026-10-02.md. Per-screen and per-Mongo-model/query/write status labeling is not yet complete.
SQL-011 | 0. Freeze SQL contract and create evidence | 0.2 Inventory all pages, endpoints and runtime entry points | Record page-specific behavior that is retained, simplified, or unavailable. | every menu page and every Mongo model/query/write has a named disposition and no untraced runtime entry point remains. | None | In Progress |  |  |  | POS behavior documented in docs/SQL_POS_PATH_AUDIT_2026-10-02.md. Other screens still need page-specific retained/simplified/unavailable behavior analysis.
SQL-012 | 1. Sales and POS | 1.1 POS terminal and SQL bill writer | Trace catalogue, barcode lookup, counters, billing limits, preview, checkout, offline queue and retry from UI to SQL. | barcode sale and supported tender persist once to the shop database; totals/stock reconcile; DB failure fails closed or queues according to the documented offline contract; no Mongo read/write occurs. | 0.1 schema verification; 0.2 page/API inventory | Blocked |  |  |  | SQL POS path traced from POSModule/usePOSLogic/usePOSCheckout → POST /api/pos/invoice/preview and /api/pos/invoice → posSql.routes.ts → PosSqlController → writePosBillToSql → dbo.sales2/salsntry. Missing erp.sales_idempotency makes exactly-once retry unsafe; missing erp.sales_return_allocation prevents durable returned-quantity/source-line checks. No end-to-end bill or DB write was performed. See docs/SQL_POS_PATH_AUDIT_2026-10-02.md and blocker B-02.
SQL-013 | 1. Sales and POS | 1.1 POS terminal and SQL bill writer | Confirm existing dbo.sales2, dbo.salsntry, product, stock, counter and GST fields match the writer's reads/writes. | barcode sale and supported tender persist once to the shop database; totals/stock reconcile; DB failure fails closed or queues according to the documented offline contract; no Mongo read/write occurs. | 0.1 schema verification; 0.2 page/API inventory | Done |  |  | 2026-10-02 | Schema snapshot confirms POS-used columns exist in sales2, salsntry, purentrydetails, newproduct, stockdetails, countername, bill_option, gstgroup, specialcondion, and return-source tables. Header/line inserts filter optional columns against live metadata; presence verified, business totals still require transaction reconciliation.
SQL-014 | 1. Sales and POS | 1.1 POS terminal and SQL bill writer | Verify erp.sales_idempotency and erp.sales_return_allocation already exist with compatible columns before retaining paths that reference them. Do not run migration 004. | barcode sale and supported tender persist once to the shop database; totals/stock reconcile; DB failure fails closed or queues according to the documented offline contract; no Mongo read/write occurs. | 0.1 schema verification; 0.2 page/API inventory | Blocked |  |  |  | Read-only schema snapshot confirms erp.sales_idempotency and erp.sales_return_allocation are absent. Per no-DDL rule neither repository migration was run; retry dedupe and exact return allocation remain blocked under B-02.
SQL-015 | 1. Sales and POS | 1.1 POS terminal and SQL bill writer | Remove any Mongo Item lookup, catalogue mirror, fallback or ObjectId dependency from the active POS path. | barcode sale and supported tender persist once to the shop database; totals/stock reconcile; DB failure fails closed or queues according to the documented offline contract; no Mongo read/write occurs. | 0.1 schema verification; 0.2 page/API inventory | Done |  |  | 2026-10-02 | Active /api/pos route is mounted to posSql.routes.ts; controller resolves barcode via SQL findByKeyDirect and inventory SQL lookup. Static call-path scan found no Mongoose Item model, ObjectId, catalogue mirror, or Mongo fallback; unrelated unmounted legacy modules are outside this path. Evidence in SQL_POS_PATH_AUDIT_2026-10-02.md.
SQL-016 | 1. Sales and POS | 1.1 POS terminal and SQL bill writer | Document current unsupported behavior: customer credit, loyalty points, and cash-book side effects; ensure checkout does not imply those were persisted. | barcode sale and supported tender persist once to the shop database; totals/stock reconcile; DB failure fails closed or queues according to the documented offline contract; no Mongo read/write occurs. | 0.1 schema verification; 0.2 page/API inventory | Done |  |  | 2026-10-02 | Controller ignores customer/loyalty fields and hard-codes hasCustomer=false; unpaid/credit tender is rejected by posTenders. Sale finance side effect is addTransaction to Redux only; no cash-book insert is in SQL POS writer. Audit documents explicit retained/unavailable behavior and avoids claiming these effects persisted.
SQL-017 | 1. Sales and POS | 1.1 POS terminal and SQL bill writer | Reconcile bill totals, GST, discounts, stock decrement, returned quantities, retries and duplicate submissions against representative SQL bills. | barcode sale and supported tender persist once to the shop database; totals/stock reconcile; DB failure fails closed or queues according to the documented offline contract; no Mongo read/write occurs. | 0.1 schema verification; 0.2 page/API inventory | Blocked |  |  |  | No representative existing bill rows were reconciled in this pass; totals/GST/discount and stock results therefore remain unverified. Exactly-once retry validation is impossible while erp.sales_idempotency is absent, and return quantity/source matching is limited by missing erp.sales_return_allocation. No bill was written; no DDL/tests run.
SQL-018 | 1. Sales and POS | 1.2 Sales register, invoice detail and receipt | Replace /api/sales-invoice/* UI dependencies with explicit SQL list/detail/report endpoints, or classify the operation unavailable. | the register shows only SQL rows with truthful totals and paging; detail/receipt match the persisted bill; unsupported mutations are visibly unavailable. | 0.1 schema verification; 0.2 page/API inventory | Done |  |  | 2026-10-02 | SQL-only app mounts /api/sales-invoice to salesSql.routes.ts. Register list, detail, and summary now return the response envelope expected by frontend reducers and read sales2/salsntry; dues are shown as unavailable where SQL summary has no dues source. Audit: docs/SQL_POS_PATH_AUDIT_2026-10-02.md.
SQL-019 | 1. Sales and POS | 1.2 Sales register, invoice detail and receipt | Map filters, pagination, invoice identifiers and line detail to existing sales2 / salsntry columns. | the register shows only SQL rows with truthful totals and paging; detail/receipt match the persisted bill; unsupported mutations are visibly unavailable. | 0.1 schema verification; 0.2 page/API inventory | In Progress |  |  |  | Added SQL paging/count with search and payment status filters; invoice IDs map through sysidandbill and line details through systemidbill. Customer filter maps sales2.cus_card to the SQL customer card-number ID, but the historical cus_card relationship has not been validated against bill rows.
SQL-020 | 1. Sales and POS | 1.2 Sales register, invoice detail and receipt | Ensure receipt/reprint reads use the SQL bill key and do not fetch Mongo Invoice, Customer or Branch documents. | the register shows only SQL rows with truthful totals and paging; detail/receipt match the persisted bill; unsupported mutations are visibly unavailable. | 0.1 schema verification; 0.2 page/API inventory | Done |  |  | 2026-10-02 | Sales invoice detail now requests receipt context with the persisted invoice SQL _id (sql:<sysidandbill>) rather than the printed invoice number. Receipt service resolves the invoice through the SQL endpoint and loads profile/branch through SQL-only routes; no Mongo Invoice/Customer/Branch fetch is used.
SQL-021 | 1. Sales and POS | 1.2 Sales register, invoice detail and receipt | Keep edit, delete and mark-paid disabled until existing SQL semantics support a safe transactional update and reversal. | the register shows only SQL rows with truthful totals and paging; detail/receipt match the persisted bill; unsupported mutations are visibly unavailable. | 0.1 schema verification; 0.2 page/API inventory | Done |  |  | 2026-10-02 | SQL invoices are read-only: register delete is disabled for sql: IDs, detail hides payment allocation and edit actions with an explanation, and mounted SQL sales routes expose GET only. SQL-only route allowlist blocks legacy PUT/DELETE operations.
SQL-022 | 1. Sales and POS | 1.3 Invoice entry form | Decide whether /sales/new can use the supported POS SQL contract without changing required business behavior. | no UI path can create an invoice only in Redux/local state or Mongo while presenting it as an SQL-saved bill. | 0.1 schema verification; 0.2 page/API inventory | Done |  |  | 2026-10-02 | Confirmed the general /sales/new form cannot preserve its customer credit, due date, free-form line item and shipping behavior via the existing POS SQL contract. Replaced the form route with an explicit unavailable state linking to POS; removed its lazy registry entry/component. SQL-only middleware permits only GET for sales-invoice and blocks legacy invoice POST.
SQL-023 | 1. Sales and POS | 1.3 Invoice entry form | If compatible, reuse the SQL POS flow and remove the parallel Mongo invoice writer; otherwise narrow the form or mark unsupported. | no UI path can create an invoice only in Redux/local state or Mongo while presenting it as an SQL-saved bill. | 0.1 schema verification; 0.2 page/API inventory | Done |  |  | 2026-10-02 | General Mongo invoice form is removed from active route/module registry. SQL-only app uses the supported POS invoice preview/write contract for counter bills; sales-invoice POST route is not mounted or allowed. Free-form customer-credit invoices are explicitly unavailable.
SQL-024 | 1. Sales and POS | 1.3 Invoice entry form | Verify customer, invoice numbering, payment, GST, discount, stock and tax behavior against existing fields before enabling each input. | no UI path can create an invoice only in Redux/local state or Mongo while presenting it as an SQL-saved bill. | 0.1 schema verification; 0.2 page/API inventory | Done |  |  | 2026-10-02 | The existing SQL field map supports the inputs enabled in POS: sales2 invoice numbering/total/tender/GST/discount/counter fields, salsntry barcode/quantity/amount/tax/discount lines, and purchase/sale/return rows for stock calculation. Customer credit, loyalty, free-form items and allocation remain disabled. Field presence from snapshot; bill-value reconciliation remains SQL-017.
SQL-025 | 1. Sales and POS | 1.4 Returns and returned-items screen | Rewire returned-item lookup from /api/pos/invoices and /api/returns to SQL /api/pos/return-sources and POS Return mode. | return/exchange cannot exceed sold quantity, original paid value is used, inventory and sales reporting agree, and no Mongo Return/Invoice/Item model is accessed. | 0.1 schema verification; 0.2 page/API inventory | Blocked |  |  |  | Legacy return entry/history screens no longer call /api/returns or /api/pos/invoices; active screen states SQL limitation. POS ReturnBillPicker already calls /api/pos/return-sources, but source lookup and checkout fail closed because required erp.sales_return_allocation is absent. B-02; do not add a table.
SQL-026 | 1. Sales and POS | 1.4 Returns and returned-items screen | Link each returned unit to its original SQL sale line and refund the paid unit value, including applied discounts and GST. | return/exchange cannot exceed sold quantity, original paid value is used, inventory and sales reporting agree, and no Mongo Return/Invoice/Item model is accessed. | 0.1 schema verification; 0.2 page/API inventory | Blocked |  |  |  | sqlPosWriter has source-line lookup, limits, original paidEach and GST logic, but it requires returnAllocations to enforce per-source quantities and persist linkage. The verified schema has no erp.sales_return_allocation, so no return is allowed. Existing table requirement unresolved; no DDL.
SQL-027 | 1. Sales and POS | 1.4 Returns and returned-items screen | Verify the existing return-allocation table is available before enabling source-line allocation; do not create it. | return/exchange cannot exceed sold quantity, original paid value is used, inventory and sales reporting agree, and no Mongo Return/Invoice/Item model is accessed. | 0.1 schema verification; 0.2 page/API inventory | Blocked |  |  |  | Read-only 2026-10-02 schema snapshot for SSS_copy has no erp.sales_return_allocation table. sqlPosWriter verifies required columns and refuses source-line allocation when unavailable. No migration or table creation was run; blocked under B-02.
SQL-028 | 1. Sales and POS | 1.4 Returns and returned-items screen | Keep standalone return create/delete routes disabled unless existing Textilesoft return tables are demonstrated to be the active return source and stock/report effects reconcile. | return/exchange cannot exceed sold quantity, original paid value is used, inventory and sales reporting agree, and no Mongo Return/Invoice/Item model is accessed. | 0.1 schema verification; 0.2 page/API inventory | Done |  |  | 2026-10-02 | Standalone Mongo-backed return screens removed from active routes; SQL return writes fail closed because erp.sales_return_allocation is absent.
SQL-029 | 1. Sales and POS | 1.5 Estimates, Sales Orders and Delivery Challans | Inspect existing SSS schema for semantically compatible estimate, order, challan, line, state, conversion and reversal storage. | each workflow is either verified end-to-end on existing SQL data or visibly unavailable; no fake-success save. | 0.1 schema verification; 0.2 page/API inventory | Done |  |  | 2026-10-02 | SSS_copy schema inventory: estimate, sales_order and delivery_challan columns/FKs recorded in SQL_POS_PATH_AUDIT_2026-10-02.md.
SQL-030 | 1. Sales and POS | 1.5 Estimates, Sales Orders and Delivery Challans | Verify key relationships and partial-fulfillment lifecycle; do not use invoice or GRN tables as substitutes. | each workflow is either verified end-to-end on existing SQL data or visibly unavailable; no fake-success save. | 0.1 schema verification; 0.2 page/API inventory | Blocked |  |  |  | All three ERP document tables are empty; JSON item/document links and only challan-to-order FK leave identity, partial fulfillment, conversion and reversal lifecycle unverified.
SQL-031 | 1. Sales and POS | 1.5 Estimates, Sales Orders and Delivery Challans | For each workflow, implement a SQL adapter only if all required records fit existing fields; otherwise retain the page with an explicit unavailable state and disable writes. | each workflow is either verified end-to-end on existing SQL data or visibly unavailable; no fake-success save. | 0.1 schema verification; 0.2 page/API inventory | Done |  |  | 2026-10-02 | Former document screens now show explicit unavailable state; no SQL adapter/write enabled without verified record and lifecycle compatibility.
SQL-032 | 1. Sales and POS | 1.5 Estimates, Sales Orders and Delivery Challans | Remove Mongo models/controllers only after routes are removed or replaced and all callers are accounted for. | each workflow is either verified end-to-end on existing SQL data or visibly unavailable; no fake-success save. | 0.1 schema verification; 0.2 page/API inventory | Done |  |  | 2026-10-02 | Removed unmounted Mongo-mixed estimate/order/challan controllers, routes, adapters and UI after static reference searches found no remaining code callers.
SQL-033 | 1. Sales and POS | 1.6 Receipts, credits, dues and MRP-pending invoices | Prove an existing stable SQL customer key before enabling any customer-linked receipt, credit or dues operation. | balances derive from persisted SQL transactions and reconcile; unsupported operations cannot mutate UI-only state or claim success. | 0.1 schema verification; 0.2 page/API inventory | Blocked |  |  |  | dbo.customercmyname has no declared primary/unique key in the captured metadata; sales2.cus_card matching card_number with sl_nu fallback has no declared FK. No live relationship reconciliation was performed.
SQL-034 | 1. Sales and POS | 1.6 Receipts, credits, dues and MRP-pending invoices | Verify existing receipt allocation and cash/bank ledgers can represent payment, partial allocation, balance change and reversal. | balances derive from persisted SQL transactions and reconcile; unsupported operations cannot mutate UI-only state or claim success. | 0.1 schema verification; 0.2 page/API inventory | Blocked |  |  |  | erp.payment_in is empty, stores methods/allocations as JSON and has no FKs; prior workflow depends on Mongo Customer, Invoice, CashbankTransaction and BankAccount.
SQL-035 | 1. Sales and POS | 1.6 Receipts, credits, dues and MRP-pending invoices | Verify existing bill fields encode MRP-pending/final states before exposing the MRP-pending page. | balances derive from persisted SQL transactions and reconcile; unsupported operations cannot mutate UI-only state or claim success. | 0.1 schema verification; 0.2 page/API inventory | Blocked |  |  |  | sales2 has status columns and InvoiceMRPMainTemp/SubTemp exist but are empty with no keys; no verified link to persisted bills or pending/final transition exists.
SQL-036 | 1. Sales and POS | 1.6 Receipts, credits, dues and MRP-pending invoices | If keys or fields are absent/ambiguous, keep customer credit, receipt allocation, dues mutation and MRP finalization unavailable; do not crosswalk IDs in an unrelated table. | balances derive from persisted SQL transactions and reconcile; unsupported operations cannot mutate UI-only state or claim success. | 0.1 schema verification; 0.2 page/API inventory | Done |  |  | 2026-10-02 | Payment, customer credit, dues and MRP-pending menu/direct routes now render unavailable; payment-in Mongo-mixed controller, route and adapter removed.
SQL-037 | 1. Sales and POS | 1.7 Sales reports and wholesale screens | Compare each sales report's SQL source tables, date semantics, cancellation filters, return treatment and totals. | reports disclose their SQL scope and reconcile to source bills; no Mongo aggregates are mixed into SQL results. | 0.1 schema verification; 0.2 page/API inventory | Blocked |  |  |  | Static report source and formula review is documented, but no representative bill/report totals or return treatment were reconciled against live SQL data.
SQL-038 | 1. Sales and POS | 1.7 Sales reports and wholesale screens | Rewire wholesale bill and report pages from Mongo /api/sales-invoice/wholesale/* to SQL only if existing rows preserve wholesale/counter/channel identifiers. | reports disclose their SQL scope and reconcile to source bills; no Mongo aggregates are mixed into SQL results. | 0.1 schema verification; 0.2 page/API inventory | Done |  |  | 2026-10-02 | Wholesale invoices/reports are not SQL-channel-safe: POS writer does not persist WholeSaleStatus, and the SQL-only app does not mount the old Mongo endpoints. Wholesale sales pages now show unavailable.
SQL-039 | 1. Sales and POS | 1.7 Sales reports and wholesale screens | Verify Wholesale Sales Entry's posted SQL payload persists the correct counter/channel and wholesale price/discount behavior. | reports disclose their SQL scope and reconcile to source bills; no Mongo aggregates are mixed into SQL results. | 0.1 schema verification; 0.2 page/API inventory | Done |  |  | 2026-10-02 | Verified WR form sends saleChannel but SQL writer ignores it; SQL invoice mapping returns RETAIL and does not apply newproduct.WR_Rate. Entry/counter flow disabled.
SQL-040 | 1. Sales and POS | 1.7 Sales reports and wholesale screens | Keep a narrower or unavailable wholesale report where SQL cannot distinguish wholesale records reliably. | reports disclose their SQL scope and reconcile to source bills; no Mongo aggregates are mixed into SQL results. | 0.1 schema verification; 0.2 page/API inventory | Done |  |  | 2026-10-02 | Wholesale sales and stock report screens now explicitly unavailable because existing SQL rows cannot be reliably filtered to that channel.
SQL-041 | 2. Product and Inventory | 2. Product and Inventory | Inventory every screen: Items, Variant Search, Categories, Product Master, Aged Stock, Batches, Barcodes, Combo Offers, Serial/IMEI, Damage/Loss, Stock Transfer, Import, Reprint and Export. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | 0.1 and 0.2; POS task 1.1 for checkout stock paths | Done |  |  | 2026-10-02 | Inventory screen/API support matrix recorded in INVENTORY_SQL_SCREEN_AUDIT_2026-10-02.md; unsupported menu/direct pages replaced by explicit unavailable state.
SQL-042 | 2. Product and Inventory | 2. Product and Inventory | Map product/attribute/catalogue reads and writes to existing shop tables; remove Item materialization, Mongo fallback and mirror paths. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | 0.1 and 0.2; POS task 1.1 for checkout stock paths | Done |  |  | 2026-10-02 | Active inventory reads are direct SQL; removed Mongo catalogue fallback reads, unused mirrored-item helper, SQL-to-Mongo sync service/CLI/API and restore-triggered sync.
SQL-043 | 2. Product and Inventory | 2. Product and Inventory | Validate stock quantity, unit, barcode, GST, price and category meanings against actual rows. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | 0.1 and 0.2; POS task 1.1 for checkout stock paths | Done |  |  | 2026-10-02 | Live read-only SSS_copy aggregates: stockdetails has 80,997 distinct nonblank barcodes, positive numeric qty/MRP ranges; mapped lookup categories/units are consistent by duplicate product code. GST anomalies (1/2 and 24 unparsable rows) are documented; no tax correctness inferred.
SQL-044 | 2. Product and Inventory | 2. Product and Inventory | For stock movement, transfer, damage/loss and serialized-unit operations, prove existing SQL event/serial tables and reverse operations before enabling writes. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | 0.1 and 0.2; POS task 1.1 for checkout stock paths | Done |  |  | 2026-10-02 | Schema snapshot and SQL route review: no enabled SQL writes for damage/loss, transfer, serial/IMEI or stock event reversal. Disabled barcode-cancel write pending verified reverse lifecycle; documented existing event tables and counts in INVENTORY_SQL_SCREEN_AUDIT_2026-10-02.md.
SQL-045 | 2. Product and Inventory | 2. Product and Inventory | Verify combo/free-item offers against existing compatible offer tables; never encode offers in unrelated product fields. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | 0.1 and 0.2; POS task 1.1 for checkout stock paths | Done |  |  | 2026-10-02 | Verified BarcodewiseComboOffer and freeproduct snapshot tables are empty and no active SQL-only offer lifecycle route exists. Combo/free-item screens remain unavailable; documented in INVENTORY_SQL_SCREEN_AUDIT_2026-10-02.md.
SQL-046 | 2. Product and Inventory | 2. Product and Inventory | Disable unsupported mutations with explicit API/UI status while preserving screens for later review. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | 0.1 and 0.2; POS task 1.1 for checkout stock paths | Done |  |  | 2026-10-02 | Items/products/search routes now use read-only SQL item lookup; unsupported inventory pages remain visible as unavailable. SQL inventory API returns SQL_INVENTORY_OPERATION_UNAVAILABLE for unsupported paths/methods, including category GET and barcode cancellation. Backend build passed.
SQL-047 | 3. Purchase and supplier workflows | 3. Purchase and supplier workflows | Inventory Register, New Entry, Express Purchase, Orders, Order List/Form, GRN, GRN Transfers, Bills, History, Returns, Debit Notes, Payments, Payment Out, Payables, Upload, Rates, PDC Vault and Cashflow. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | 0.1 and 0.2; verify supplier identity for linked flows | Done |  |  | 2026-10-02 | Inventoried all listed purchase screens, paths, modules, and mounted SQL APIs in docs/PURCHASE_SQL_SCREEN_INVENTORY_2026-10-02.md; not yet a behavior validation (covered by SQL-048 onward).
SQL-048 | 3. Purchase and supplier workflows | 3. Purchase and supplier workflows | Verify SQL purchase-entry and purchase-return routes against current Textilesoft GRN/return tables, including stock and deletion/reversal behavior. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | 0.1 and 0.2; verify supplier identity for linked flows | Done |  |  | 2026-10-02 | Read-only SSS_copy aggregates and source review found 26 active purchase lines without stockdetails rows, 4/8 return lines without purchase-barcode links, and one duplicated return number. GRN and return create/delete are disabled; return detail now rejects duplicate/unlinked source data. See docs/PURCHASE_SQL_SCREEN_INVENTORY_2026-10-02.md.
SQL-049 | 3. Purchase and supplier workflows | 3. Purchase and supplier workflows | Trace purchase order, GRN transfer, bill and supplier-payment IDs through all screens; verify a stable existing supplier key. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | 0.1 and 0.2; verify supplier identity for linked flows | Blocked |  |  |  | supplierdetail has 114 rows, no PK/unique index, and four duplicate-name groups; purgrnentry stores supplier_name text. Order/transfer/payment routes are not mounted. Stable supplier key is unproven; blocked under B-01. See docs/PURCHASE_SQL_SCREEN_INVENTORY_2026-10-02.md.
SQL-050 | 3. Purchase and supplier workflows | 3. Purchase and supplier workflows | Inspect existing SQL fields/tables for debit notes, rate revisions, payment-out, cheque states, supplier ageing and reconciliation. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | 0.1 and 0.2; verify supplier identity for linked flows | Done |  |  | 2026-10-02 | Existing erp.debit_note/rate_revision/payment_out/purchase_payment/supplier_reconciliation tables are empty; supplier_group_member is absent, and no cheque/payables/supplier-ageing APIs are mounted. Unsupported purchase modules and API paths now return explicit unavailable states.
SQL-051 | 3. Purchase and supplier workflows | 3. Purchase and supplier workflows | Remove Mongo Supplier/Bill/Purchase lookups from SQL handlers or disable operations with unresolved joins. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | 0.1 and 0.2; verify supplier identity for linked flows | Done |  |  | 2026-10-02 | Active SQL-only app mounts purchase list, purchase-entry reads and purchase-return reads; those SQL handlers use SQL adapters only. Mongo Supplier/Bill/Purchase handlers remain unmounted and are not reachable from these SQL routes.
SQL-052 | 3. Purchase and supplier workflows | 3. Purchase and supplier workflows | Do not treat a stored payment as complete unless the existing SQL bill balance, account balance and reversal semantics are represented. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | 0.1 and 0.2; verify supplier identity for linked flows | Done |  |  | 2026-10-02 | Payment-out/payables/cheque/cashflow pages and APIs are unavailable. Purchase-return rows now display as recorded return value with payment state untracked and supplier balance unreconciled; payment type is no longer treated as proof of settlement.
SQL-053 | 4. Customers, suppliers and loyalty | 4. Customers, suppliers and loyalty | Verify stable, unique, immutable existing customer and supplier identifiers from schema metadata and deployed write-path evidence. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | 0.1 and 0.2; Sales task 1.6 | Blocked |  |  |  | No verified unique immutable customer or supplier key; customer key fields are nullable and supplier name duplicates exist. Screen actions remain disabled; no schema changes allowed.
SQL-054 | 4. Customers, suppliers and loyalty | 4. Customers, suppliers and loyalty | Map directory fields, search, edit, group membership, ledger, statement, referral/consent and archive behavior one field at a time. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | 0.1 and 0.2; Sales task 1.6 | Done |  |  | 2026-10-02 | Documented customer/supplier fields, mounted route behavior, and unsupported group, ledger, statement, referral, consent and archive semantics in docs/CUSTOMER_SUPPLIER_SQL_SCREEN_AUDIT_2026-10-02.md.
SQL-055 | 4. Customers, suppliers and loyalty | 4. Customers, suppliers and loyalty | Trace customer references in invoices, sales returns, receipts, dues, loyalty and reports; remove Mongo ObjectId conversion/validation on SQL paths. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | 0.1 and 0.2; Sales task 1.6 | Done |  |  | 2026-10-02 | SQL customer detail now rejects ambiguous keys; POS lookup/create no longer calls Mongo-shaped search/create endpoints or creates local fake IDs. Party screens disabled.
SQL-056 | 4. Customers, suppliers and loyalty | 4. Customers, suppliers and loyalty | Map points transactions to existing customer-point tables only if earn/redeem/reverse history and balances are compatible. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | 0.1 and 0.2; Sales task 1.6 | Done |  |  | 2026-10-02 | Mapped existing point tables as configuration without compatible earn/redeem/reversal history; disabled POS points preview and loyalty actions.
SQL-057 | 4. Customers, suppliers and loyalty | 4. Customers, suppliers and loyalty | If stable ID or ledger semantics cannot be proven, disable linked customer mutations; allow only explicitly anonymous SQL billing. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | 0.1 and 0.2; Sales task 1.6 | Done |  |  | 2026-10-02 | Disabled customer/supplier mutations and linked screens; POS clearly remains anonymous. Backend build and frontend typecheck pass.
SQL-058 | 5. Finance and expenses | 5. Finance and expenses | Inventory Finance pages: Overview, Cash, Bank, Petty Cash, Transfers, Reconciliation, Summary, Loans, Goals, Statements, SMS Tracker, GST, Journal, EMI Plans and Card Terminals. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | 0.1 and 0.2; Sales, Purchase and Customer dependencies | Done |  |  | 2026-10-02 | Inventoried Finance pages and mounted read-only SQL cash/bank, cheque and daily-finance APIs; disabled mixed/unsupported Finance UI routes. See docs/FINANCE_EXPENSE_SQL_SCREEN_AUDIT_2026-10-02.md.
SQL-059 | 5. Finance and expenses | 5. Finance and expenses | Inventory Expenses pages: Tracker, Categories, Recurring and Reports; separate operational entry from SQL read-only reports. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | 0.1 and 0.2; Sales, Purchase and Customer dependencies | Done |  |  | 2026-10-02 | Separated expense read/report data from operational entry, categories and recurring screens; entry APIs unavailable and unsafe SQL create/update/delete adapter removed.
SQL-060 | 5. Finance and expenses | 5. Finance and expenses | Trace each screen to existing SQL transaction tables and fields for cash/bank, bills, receipts, cheques, loans, journals, GST, petty-cash close, budgets and recurring schedules. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | 0.1 and 0.2; Sales, Purchase and Customer dependencies | Done |  |  | 2026-10-02 | Mapped dbo.expenseentry source columns and missing receipt/user/tenant/account/approval/reversal fields; documented SQL finance table sources and unsupported lifecycles.
SQL-061 | 5. Finance and expenses | 5. Finance and expenses | Verify opening/current balances, transfer pairs, reconciliation state, dates, void/reversal handling and account identity. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | 0.1 and 0.2; Sales, Purchase and Customer dependencies | Blocked |  |  |  | Live sample close and bank statement were unavailable for opening/current balance, transfer-pair, void and reconciliation validation. Operational Finance screens are disabled; do not present report outputs as reconciled balances.
SQL-062 | 5. Finance and expenses | 5. Finance and expenses | Compare SQL report calculations to the exact enabled source set and disclose exclusions; remove Mongo-sourced rows from combined reports. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | 0.1 and 0.2; Sales, Purchase and Customer dependencies | Done |  |  | 2026-10-02 | Audited SQL report source sets and disclosed exclusions and assumptions: expense amount uses exoutamt, payment mode defaults cash, void state is unmapped; Finance reports use SQL only.
SQL-063 | 5. Finance and expenses | 5. Finance and expenses | Reuse existing dbo.expenseentry and category tables only after validating keys, fields and lifecycle; keep recurring behavior unavailable if no compatible schedule table exists. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | 0.1 and 0.2; Sales, Purchase and Customer dependencies | Done |  |  | 2026-10-02 | Expense categories now read existing dbo.expensegroup/dbo.expensename via SQL master mapping; no budget/approval/recurring behavior is inferred and write handlers are unavailable.
SQL-064 | 5. Finance and expenses | 5. Finance and expenses | Remove Mongo Bill, BankAccount, Expense and finance model queries from enabled SQL report and operation paths. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | 0.1 and 0.2; Sales, Purchase and Customer dependencies | Done |  |  | 2026-10-02 | Enabled finance report and cash/bank routes use SQL adapters only; expense and finance Mongo model paths are outside the SQL route graph. See finance screen audit.
SQL-065 | 6. HR, payroll and commission | 6. HR, payroll and commission | Inventory Staff Management, Payroll, Allowances, Attendance, Daily Board, Payslips, Salary Structures, Advances and Commission screens. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | 0.1 and 0.2 | Done |  |  | 2026-10-02 | Inventoried staff, payroll, allowances, attendance, daily board, payslips, salary structure, advances and commission screens; unsupported HR workflows now display unavailable state.
SQL-066 | 6. HR, payroll and commission | 6. HR, payroll and commission | Verify existing employee identifier and compatible attendance, payroll-period, component, deduction, payment and payslip fields. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | 0.1 and 0.2 | Blocked |  |  |  | Read-only live audit found zero dbo.newemployee rows and no primary/unique index on code; code generation uses MAX+1. No stable employee key can be verified.
SQL-067 | 6. HR, payroll and commission | 6. HR, payroll and commission | Map each workflow; do not infer payroll storage from the presence of an employee table. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | 0.1 and 0.2 | Done |  |  | 2026-10-02 | Mapped newemployee master versus absent attendance/pay-period/payroll/payslip/payment lifecycles; HR writes and workflows disabled instead of persisting unsupported data.
SQL-068 | 6. HR, payroll and commission | 6. HR, payroll and commission | Verify commission inputs (invoice, product/category, employee/user), calculation basis and payout history against existing SQL data. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | 0.1 and 0.2 | Blocked |  |  |  | Commission rules have no employee FK and no payout ledger; dbo.newemployee is empty and code linkage to salsntry.sls_man cannot be verified. Commission UI remains unavailable.
SQL-069 | 6. HR, payroll and commission | 6. HR, payroll and commission | Where no compatible existing SQL transaction table exists, keep the operation explicitly unavailable; do not persist payroll JSON in employee notes/config. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | 0.1 and 0.2 | Done |  |  | 2026-10-02 | Disabled payroll, attendance, payslip, allowance, advance and commission workflows when compatible SQL transaction lifecycles are absent; removed HR SQL writes.
SQL-070 | 7. Offers, marketing and communications | 7. Offers, marketing and communications | Inventory Combo Offers, free-product/quantity schemes, discount configuration, coupons and offer reporting. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | 0.1 and 0.2; Inventory and Customer identity where linked | Done |  |  | 2026-10-02 | Inventoried combo/free-item, discount, coupon and campaign screens; unsupported offer and campaign screens now show unavailable. See docs/COMMISSION_OFFERS_SQL_AUDIT_2026-10-02.md.
SQL-071 | 7. Offers, marketing and communications | 7. Offers, marketing and communications | Verify existing offer tables support eligibility, dates, product/barcode scope, minimum spend/quantity, free quantity, redemption and invoice linkage. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | 0.1 and 0.2; Inventory and Customer identity where linked | Blocked |  |  |  | dbo.BarcodewiseComboOffer has zero rows and no verified eligibility/date/redemption/invoice-link/reversal lifecycle; no compatible offer master is available.
SQL-072 | 7. Offers, marketing and communications | 7. Offers, marketing and communications | Verify the SQL bill rows preserve which offer was applied before enabling offer-performance reports. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | 0.1 and 0.2; Inventory and Customer identity where linked | Blocked |  |  |  | SQL POS writer does not populate legacy OfferQty/SchemaDiscount/comboname fields; applied offer cannot be traced to a bill. Offer reports stay disabled.
SQL-073 | 7. Offers, marketing and communications | 7. Offers, marketing and communications | Inventory WhatsApp campaigns/templates, marketing, SMS tracker, social integrations, email and storefront separately from external provider connectivity. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | 0.1 and 0.2; Inventory and Customer identity where linked | Done |  |  | 2026-10-02 | Inventoried campaign/templates, WhatsApp, SMS, social, email and storefront screens; all are routed to unavailable where no mounted SQL lifecycle exists.
SQL-074 | 7. Offers, marketing and communications | 7. Offers, marketing and communications | Reuse existing SQL campaign/log tables only if they store the actual required lifecycle; otherwise retain honest not-connected states and disable persistence actions. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | 0.1 and 0.2; Inventory and Customer identity where linked | Done |  |  | 2026-10-02 | No mounted campaign/log route was found for the existing SQL sources; screens remain unavailable and external provider connectivity is not reported as campaign history.
SQL-075 | 7. Offers, marketing and communications | 7. Offers, marketing and communications | Remove Mongo campaign, MetaIntegration, WhatsApp, SMS and combo model usage after all API callers are accounted for. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | 0.1 and 0.2; Inventory and Customer identity where linked | Done |  |  | 2026-10-02 | Removed unmounted Mongo Meta, WhatsApp campaign/template, SMS tracker, combo-offer and engagement-report runtime files and route references after caller search.
SQL-076 | 8. System, audit, sync and administration | 8. System, audit, sync and administration | Inventory General Settings, Master Data, Branch/Store settings, Users/Roles, Discount Limits, Tenants, Audit, Sync and Restore. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | 0.1 and 0.2; domain waves for enabled features | Done |  |  | 2026-10-02 | Inventoried settings, user/org, discount, audit, sync, restore, tenant and master-data routes; unsupported settings/admin screens now show SQL-unavailable state.
SQL-077 | 8. System, audit, sync and administration | 8. System, audit, sync and administration | Keep verified SQL auth/user/org routes; map each settings field only to an existing compatible SQL column/key contract. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | 0.1 and 0.2; domain waves for enabled features | Done |  |  | 2026-10-02 | Documented and retained SQL auth/newuser, limited user/name and discount-limit fields, companydetail business profile, Textilesoft org masters and explicit SQL master allowlist.
SQL-078 | 8. System, audit, sync and administration | 8. System, audit, sync and administration | Verify audit storage can represent actor, entity, action, timestamp and change data before claiming audit completeness. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | 0.1 and 0.2; domain waves for enabled features | Not Started
SQL-079 | 8. System, audit, sync and administration | 8. System, audit, sync and administration | Verify sync cursor/conflict/device/ledger state has an existing compatible representation; otherwise disable sync actions and remove Mongo timers/workers. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | 0.1 and 0.2; domain waves for enabled features | Not Started
SQL-080 | 8. System, audit, sync and administration | 8. System, audit, sync and administration | Verify restore targets and recovery workflows use only SQL and do not invoke Mongo backup/restore tooling. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | 0.1 and 0.2; domain waves for enabled features | Not Started
SQL-081 | 8. System, audit, sync and administration | 8. System, audit, sync and administration | Remove Mongo tenant lookup, auth type/runtime dependency, settings and audit queries from the active route graph. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | 0.1 and 0.2; domain waves for enabled features | Not Started
SQL-082 | 9. Remove Mongo code and runtime dependencies | 9. Remove Mongo code and runtime dependencies | Enumerate every remaining mongoose, mongodb, MongoClient, ObjectId, MONGO_*, mirror and fallback reference; classify type-only, docs, tests, scripts and runtime separately. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | Waves 1-8 complete or feature explicitly unavailable | Not Started
SQL-083 | 9. Remove Mongo code and runtime dependencies | 9. Remove Mongo code and runtime dependencies | Remove unreachable legacy route mounts, Mongo controllers/services/repositories/models/interfaces and their tests after confirming no imports/callers remain. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | Waves 1-8 complete or feature explicitly unavailable | Not Started
SQL-084 | 9. Remove Mongo code and runtime dependencies | 9. Remove Mongo code and runtime dependencies | Remove Mongo seed/migration/backup/restore scripts from supported operations; archive any approved one-time export tooling outside the application runtime and without credentials. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | Waves 1-8 complete or feature explicitly unavailable | Not Started
SQL-085 | 9. Remove Mongo code and runtime dependencies | 9. Remove Mongo code and runtime dependencies | Remove Mongo package dependencies, environment variables, Docker services/volumes, health checks and deployment documentation. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | Waves 1-8 complete or feature explicitly unavailable | Not Started
SQL-086 | 9. Remove Mongo code and runtime dependencies | 9. Remove Mongo code and runtime dependencies | Remove stale Mongo assumptions from frontend API clients/types and validate every remaining menu item routes to SQL or a clear unavailable state. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | Waves 1-8 complete or feature explicitly unavailable | Not Started
SQL-087 | 9. Remove Mongo code and runtime dependencies | 9. Remove Mongo code and runtime dependencies | Run backend/frontend type checks, builds, relevant tests and static scans; perform a staging run with Mongo unreachable and no Mongo credentials. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | Waves 1-8 complete or feature explicitly unavailable | Not Started
SQL-088 | 9. Remove Mongo code and runtime dependencies | 9. Remove Mongo code and runtime dependencies | Verify SQL credentials cannot perform DDL and no migration command is invoked at startup or deployment. | Complete the task and record evidence that the page/API uses only verified existing SQL objects. | Waves 1-8 complete or feature explicitly unavailable | Not Started

## Blockers
Blocker ID | Blocker | Blocks | Resolution evidence | Status | Owner | Notes
B-01 | Customer SQL key is not proven stable/unique for all linked workflows | Customer CRUD, credit sales, receipts, dues, loyalty, customer reports | Existing deployed allocation/write-path evidence and end-to-end joins; no crosswalk table | Open
B-02 | POS SQL writer references existing `erp.sales_idempotency` and `erp.sales_return_allocation` | POS retry safety and exact return-to-sale allocation | Read-only proof of deployed objects and compatible definitions; never apply migration 004 | Open |  | Also missing erp.supplier_group_member, referenced by sqlPartyReports.ts; no migration permitted.
B-03 | Sales Orders, Estimates and Delivery Challans lack confirmed compatible SQL lifecycle storage | Those transactional screens | Table/column/key/state mapping with data evidence, or explicit reduced/unavailable behavior | Open
B-04 | Receipts, supplier payments and bank/cash effects need linked SQL ledger semantics | Payment-in/out, dues, payables and balances | Verified existing allocation/account ledger tables and reconciled sample transactions | Open
B-05 | Several pages call legacy API paths while SQL-only app mounts different routes | UI/API completion across all waves | Endpoint-level route map and UI rewiring | Open
B-06 | HR/payroll, audit, sync, marketing persistence have no verified full SQL target | Those workflows | Existing compatible SQL object evidence or accepted unavailable states | Open
B-07 | Elevated erp_admin credentials remain available to the backend runtime and grant-recovery path | SQL least privilege and task SQL-002 | Remove elevated credentials from normal runtime or provide a separately controlled provisioning process; verify runtime principals have no DDL | Open | Backend/DBA | erp_admin is sysadmin/db_owner/db_ddladmin in SSS_copy; no permission changes made.
B-08 | Separate ERP_SQL database connection is not configured | Any workflow requiring a separate ERP-owned SQL database | Configure and verify an existing separate SQL database only if required; no table creation or schema changes | Open | Backend/DBA | ERP_SQL_DB_NAME/user/password are absent; check:erp-sql stops before connecting. Existing SSS erp.* adapters use SSS_copy.